## Sprint1
User Story Number | User Story | Task Number | Task | Detailed Description | Dependency | Story Points | Team Member | Provisional: | Day 1- Mon Oct 16 | Day 2- Tues Oct 17 | Day 3- Wed Oct 18 | Day 4- Thurs Oct 19 | Day 5- Fri Oct 19 | Day 6- Sat Oct 20 | Day 7- Sun Oct 21 | Actual: | Day 1- Mon Oct 16 | Day 2- Tues Oct 17 | Day 3- Wed Oct 18 | Day 4- Thurs Oct 19 | Day 5- Fri Oct 19 | Day 6- Sat Oct 20 | Day 7- Sun Oct 21
1 | As Sohee Kang (professor), I need to create accounts for students and TA's' so that they can access quizzes remotely | 1 | mock webpage to login that links to a student or instructor button | pictures for background, using forms, buttons, links on html |  | 1 | Jinming | [6 empty] | 1 | [7 empty] | 1
|  | 2 | student login mock webpage that requests username and password | pictures for background, using forms, buttons, links on html | t4 | 1 | Jinming | [7 empty] | 1 | [7 empty] | 8
|  | 3 | instructor/ta login mock webpage that requests username and password | pictures for background, using forms, buttons, links on html | t5 | 1 | Jinming | [7 empty] | 1 | [7 empty] | 0.5
|  | 4 | database that keeps student logins and password | using mysql create database, create tables, setup user accounts |  | 1 | Linhai |  |  |  |  | 1 | [7 empty] | 1
|  | 5 | database that keeps instructor/ta logins and password | using mysql create database, create tables, setup user accounts |  | 1 | Linhai |  |  |  |  | 1 | [7 empty] | 1
|  | 6 | create an admin account with username and password for the database | create sql query to insert into table | t4, t5 | 0.5 | Linhai |  |  |  |  | 0.5 | [7 empty] | 0.5
|  | 7 | welcome mock webpage (after login) (add a side bar with all links, a welcome message,etc) (dependency only to make connection, page can still be made) | create nav bar side bar, create css document for global side bar, | t1, t3 | 2 | Calvin | [5 empty] | 1 | 1 | [6 empty] | 1 | 1 | 1
|  | 8 | a mock webpage to create student accounts (excel upload) | used html forms to input information, and input excel file using html forms, custom css for formatting |  | 1 | Shoaib |  |  |  |  | 1 | [7 empty] | 1
|  | 9 | a mockpage to create ta accounts (excel upload) | used html forms to input information, and input excel file using html forms, custom css for formatting |  | 1 | Shoaib |  |  |  |  | 1 | [7 empty] | 1
|  | 10 | create dummy student and dummy ta account | create sql query to insert into table | t4 | 0.5 | Linhai |  |  |  |  | 0.5 | [7 empty] | 0.5
|  | 11 | get all login pages working, that lets admin, students and ta's login |  |  | 0
2 | As Sohee Kang (professor), I need to create an assignment for each lesson/chapter with the start date and end date | 12 | create a mock up webpage for creating assignments with the name of the assignment, start and end date | using forms on html, using javascript for the submit button |  | 1 | Yathan | [5 empty] | 1 | [7 empty] | 1
|  | 13 | make a page that lists all created assignments and start and end date, number of questions | use php to pass the data to the next html file that lists all created assignments |  | 1 | Yathan | [5 empty] | 1 | [7 empty] | 1
[6 empty] | 12 |  |  | 0 | 0 | 0 | 5 | 3 | 2 | 2 |  | 0 | 0 | 0 | 5 | 3 | 2 | 9.5

## Burndown Chart
Burndown Chart
Day | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7
Provisional | 12 | 12 | 12 | 12 | 7 | 5 | 2 | 0
Actual | 12 | 12 | 12 | 12 | 7 | 5 | 4 | 0