## Sprint Plan and Sprint Report
User Story Number | User Story | Task Number | Task | Detailed Information | Dependency | Story Points | Team Member | Provisional: | Day 1- Mon Nov 20 | Day 2- Tues Nov 21 | Day 3- Wed Nov 22 | Day 4- Thurs Nov 23 | Day 5- Fri Nov 24 | Day 6- Sat Nov 25 | Day 7- Sun Nov 26 | Actual: | Day 1- Mon Nov 20 | Day 2- Tues Nov 21 | Day 3- Wed Nov 22 | Day 4- Thurs Nov 23 | Day 5- Fri Nov 24 | Day 6- Sat Nov 25 | Day 7- Sun Nov 26
EXTRAS |  | 1 | clean up css | make sure css is responsive as reacts as expected (remove unnecessary stuff) and make the website look nice and usable |  | 5 | Yathan |  |  |  | 5
|  | 2 | bug testing | test all sections of the website, login, student account creation, assignment creation, question creation, student taking a quiz, etc to make sure it works as expected |  | 5 | Jinming | [6 empty] | 5
|  | 3 | style fix | make sure code is commented and nicely formted |  | 3 | Calvn | [6 empty] | 3
|  | 4 | set up one proper assignment with 10 questions | clean up existing assignments and questions and make 1 or 2 good assignments for demo purposes |  | 2 | Linhai | [6 empty] | 2
[6 empty] | 15 |  |  | 0 | 0 | 5 | 0 | 0 | 10 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Burndown Chart
Burndown Chart
Day | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7
Provisional | 15 | 15 | 15 | 10 | 10 | 10 | 0 | 0
Actual | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15

## Taskboard Snapshots
Taskboard Beginning: | Taskboard Ending: