## Sprint Plan and Sprint Report
User Story Number | User Story | Task Number | Task | Detailed Information | Dependency | Story Points | Team Member | Provisional: | Day 1- Mon Oct 30 | Day 2- Tues Oct 31 | Day 3- Wed Nov 1 | Day 4- Thurs Nov 2 | Day 5- Fri Nov 3 | Day 6- Sat Nov 4 | Day 7- Sun Nov 5 | Actual: | Day 1- Mon Oct 30 | Day 2- Tues Oct 31 | Day 3- Wed Nov 1 | Day 4- Thurs Nov 2 | Day 5- Fri Nov 3 | Day 6- Sat Nov 4 | Day 7- Sun Nov 5
1 | As Sohee Kang (professor), I need to create accounts for students and TA's' so that they can access quizzes remotely | 1 | Get login pages to poll the login backend | [8 empty] | 3
|  | 2 | Create a backend call to create student accounts | [10 empty] | 1
|  | 3 | Create a backend call to create TA accounts | [10 empty] | 1
|  | 4 | Get TA Account creation working with the backend | [11 empty] | 1
|  | 5 | Get Student Account Creation working with the backend | [11 empty] | 1
2 | As Sohee Kang (professor), I need to create an assignment for each lesson/chapter with the start date and end date | 6 | Create a backend call to create assignments | [8 empty] | 1 |  | 1
|  | 7 | Get assignment creation working with the backend | [9 empty] | 3
|  | 8 | Create a backend call to list assignments | [8 empty] | 1 |  | 1
|  | 9 | Get assignment list to pull data from the backend | [9 empty] | 3
3 | As Sohee Kang (professor) or Adrian Lal (TA), I need to be able to create questions such as multiple choice, text input with the correct solution and the grade weight to each assignment | 10 | Create a backend call to list questions | [10 empty] | 1
|  | 11 | Create a backend call to create questions | [10 empty] | 1
|  | 12 | Create a page for a specific assignment which will list the questions in the assignment | [10 empty] | 3
|  | 13 | Create a page to create questions for an assignment | [10 empty] | 2
4 | As Sohee Kang (professor), I need to be able to edit questions and answers after creation | 14 | Create a backend call to edit questions
|  | 15 | Create a page to edit questions from | [10 empty] | 2
5 | As Bob Sponge (student), I need to be able to take a quiz for each lesson | 16 | Create a template page that can be filled in for multiple choice | [7 empty] | 1
|  | 17 | Create a template page for short answer | [7 empty] | 1
|  | 18 | Create a backend call to return Question HTML | [10 empty] | 2
|  | 19 | Create a Backend call to accept question responses | [10 empty] | 2
|  | 20 | Create a page for 10 questions | [7 empty] | 1
[6 empty] | 0 |  |  | 0 | 0 | 3 | 5 | 6 | 17 | 2

## Burndown Chart
Burndown Chart
Day | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7
Provisional | 18.5 | 16 | 9 | 7.5 | 6 | 6 | 6 | 4
Actual | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5