## Sprint Plan and Sprint Report
User Story Number | User Story | Task Number | Task | Detailed Information | Dependency | Story Points | Team Member | Provisional: | Day 1- Mon Nov 06 | Day 2- Tues Nov 07 | Day 3- Wed Nov 08 | Day 4- Thurs Nov 09 | Day 5- Fri Nov 08 | Day 6- Sat Nov 10 | Day 7- Sun Nov 11 | Actual: | Day 1- Mon Nov 06 | Day 2- Tues Nov 07 | Day 3- Wed Nov 08 | Day 4- Thurs Nov 09 | Day 5- Fri Nov 08 | Day 6- Sat Nov 10 | Day 7- Sun Nov 11
1 | As Sohee Kang (professor), I need to create accounts for students and TA's' so that they can access quizzes remotely | 1 | front end needs to be connected with backend, so that accounts can be created |  |  | 2 | Jinming |  |  |  |  | 2
6 | As Sohee Kang (professor), I want each assignment/quiz to have randomized questions so that students don't have the same quiz | 2 | randomized list on backend and send it to frontend |  |  | 2 | Linhai | [6 empty] | 2
7 | As Sohee Kang (professor), I need students to be able to retake a quiz as many times as they want | 3 | delete old answers in sql database, it will automatically let you take another quiz |  |  | 1 | Linhai | [6 empty] | 1
8 | As Bob Sponge (student), I want to be able to see my grades for each quiz | 4 | update assignment list (student) html to pull from backend grades |  | t5 | 1 | Yathan | [7 empty] | 1
|  | 5 | backend that will calculate grades and return average |  |  | 2 | Linhai | [6 empty] | 2
9 | As Dr. Aus (professor), I need to be able to see the students' grade for each quiz | 6 | update assignment list html to pull from backend grades of total student average |  | t7 | 1 | Yathan | [7 empty] | 1
|  | 7 | backend that will calculate grades and return average of all students grades |  |  | 2 | Linhai | [6 empty] | 2
EXTRAS |  | 8 | clean up CSS |  |  | 2 | Calvin |  |  |  | 2
|  | 9 | refactor code |  |  | 5
|  | 10 | plan out testing |  |  | 1
|  | 11 | write bash script to let you pull from certain commits |  |  | 2 | Linhai | [6 empty] | 2
[6 empty] | 21 |  |  | 0 | 0 | 2 | 2 | 0 | 9 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Burndown Chart
Burndown Chart
Day | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7
Provisional | 21 | 21 | 21 | 19 | 17 | 17 | 8 | 6
Actual | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21

## Taskboard Snapshots
Taskboard Beginning: | Taskboard Ending: