## Sprint2
User Story Number | User Story | Task Number | Task | Detailed Information | Dependency | Story Points | Team Member | Provisional: | Day 1- Mon Oct 23 | Day 2- Tues Oct 24 | Day 3- Wed Oct 25 | Day 4- Thurs Oct 26 | Day 5- Fri Oct 27 | Day 6- Sat Oct 28 | Day 7- Sun Oct 29 | Actual: | Day 1- Mon Oct 23 | Day 2- Tues Oct 24 | Day 3- Wed Oct 25 | Day 4- Thurs Oct 26 | Day 5- Fri Oct 27 | Day 6- Sat Oct 28 | Day 7- Sun Oct 29
1 | As Sohee Kang (professor), I need to create accounts for students and TA's' so that they can access quizzes remotely | 1 | Figure out how Django works, and then teach everyone else/or make calls |  |  | 5 | Linhai Yin |  |  | 5
|  | 2 | Login page login button to call login function and then send to welcome page if correct | If verified account using JS (not working), send to welcome page otherwise update login page with an error |  | 2 | Jinming |  |  | 2
|  | 3 | Link in welcome page to assignment list |  |  | 0.5 | Calvin |  |  |  |  | 0.5
|  | 4 | Link in welcome page to create student account |  |  | 0.5 | Calvin |  |  |  |  | 0.5
|  | 5 | Link in welcoime page to create TA account |  |  | 0.5 | Calvin |  |  |  |  | 0.5
|  | 6 | Improve consistency of login/welcome page | CSS only |  | 2 | Calvin | [7 empty] | 2
|  | 7 | Change Navbar to be topbar only |  |  | 0.5 | Shoaib |  | 0.5
|  | 8 | Create a new webpage with just navbar and update all the other pages |  | T7 | 1 | Shoaib |  | 1
|  | 9 | Student Account Creation page add navbar |  | T7,T8 | 0.5 | Shoaib |  | 0.5
|  | 10 | TA Account Creation Page add navbar |  | T7,T8 | 0.5 | Shoaib |  | 0.5
2 | As Sohee Kang (professor), I need to create an assignment for each lesson/chapter with the start date and end date | 11 | Add Sidebar/navbar to assignment list page |  | T7,T8 | 0.5 | Yathan |  |  |  | 0.5
|  | 12 | Add Sidebar/navbar to per assignment page |  | T7,T8 | 0.5 | Yathan |  |  |  | 0.5
|  | 13 | Add a fake filled list of assignments to the mockup |  |  | 0.5 | Yathan |  |  |  | 0.5
3 | As Sohee Kang (professor) or Adrian Lal (TA), I need to be able to create questions such as multiple choice, text input with the correct solution and the grade weight to each assignment | 14 | Create a page for a specific assignment which will list the questions in the assignment |  |  | 2
|  | 15 | Create a page to create questions for an assignment |  | T13 | 2
[6 empty] | 18.5 |  |  | 2.5 | 7 | 1.5 | 1.5 | 0 | 0 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Burndown Chart
Burndown Chart
Day | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7
Provisional | 18.5 | 16 | 9 | 7.5 | 6 | 6 | 6 | 4
Actual | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5