## Sprint Plan and Sprint Report
User Story Number | User Story | Task Number | Task | Detailed Information | Dependency | Story Points | Team Member | Provisional: | Day 1- Mon Nov 20 | Day 2- Tues Nov 21 | Day 3- Wed Nov 22 | Day 4- Thurs Nov 23 | Day 5- Fri Nov 24 | Day 6- Sat Nov 25 | Day 7- Sun Nov 26 | Actual: | Day 1- Mon Nov 20 | Day 2- Tues Nov 21 | Day 3- Wed Nov 22 | Day 4- Thurs Nov 23 | Day 5- Fri Nov 24 | Day 6- Sat Nov 25 | Day 7- Sun Nov 26
EXTRAS |  | 1 | clean up css | make sure css is responsive as reacts as expected |  | 1 | Yathan |  |  |  | 1
|  | 2 | bug testing |  |  | 1 | Jinming | [6 empty] | 1
|  | 3 | style fix |  |  | 1 | Calvn | [6 empty] | 1
|  | 4 | set up one proper assignment with 10 questions |  |  | 1 | Linhai | [6 empty] | 1
|  | 5 | refactoring code/ following design patterns
[6 empty] | 4 |  |  | 0 | 0 | 1 | 0 | 0 | 3 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Burndown Chart
Burndown Chart
Day | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7
Provisional | 4 | 4 | 4 | 3 | 3 | 3 | 0 | 0
Actual | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4

## Taskboard Snapshots
Taskboard Beginning: | Taskboard Ending: