## Sprint Plan and Sprint Report
User Story Number | User Story | Task Number | Task | Detailed Information | Dependency | Story Points | Team Member | Provisional: | Day 1- Mon Oct 30 | Day 2- Tues Oct 31 | Day 3- Wed Nov 1 | Day 4- Thurs Nov 2 | Day 5- Fri Nov 3 | Day 6- Sat Nov 4 | Day 7- Sun Nov 5 | Actual: | Day 1- Mon Oct 30 | Day 2- Tues Oct 31 | Day 3- Wed Nov 1 | Day 4- Thurs Nov 2 | Day 5- Fri Nov 3 | Day 6- Sat Nov 4 | Day 7- Sun Nov 5
1 | As Sohee Kang (professor), I need to create accounts for students and TA's' so that they can access quizzes remotely | 1
2
3
4
5
6
7
8
9
10
2 | As Sohee Kang (professor), I need to create an assignment for each lesson/chapter with the start date and end date | 11
12
13
3 | As Sohee Kang (professor) or Adrian Lal (TA), I need to be able to create questions such as multiple choice, text input with the correct solution and the grade weight to each assignment | 14 | Create a page for a specific assignment which will list the questions in the assignment
|  | 15 | Create a page to create questions for an assignment
4 | As Sohee Kang (professor), I need to be able to edit questions and answers after creation
5 | As Bob Sponge (student), I need to be able to take a quiz for each lesson
6 | As Sohee Kang (professor), I want each assignment/quiz to have randomized questions so that students don't have the same quiz

## Burndown Chart
Burndown Chart
Day | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7
Provisional | 18.5 | 16 | 9 | 7.5 | 6 | 6 | 6 | 4
Actual | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5 | 18.5